## Sheet1
Date | Weekday | ToDo | Notes
2022-11-05 | Sat
2022-11-06 | Sun
2022-11-07 | Mon | HRI-Seminar, 5+ paper summaries
2022-11-08 | Tue | HRI-Seminar, rough presentation outline
2022-11-09 | Wed | Kann ich das glauben Seminar, read paper and summarize
2022-11-10 | Thu | Kann ich das glauben Seminar, create presentation
2022-11-11 | Fri | LSTM, Clean up code, remove unnecessary stuff, make naming conventions clear
2022-11-12 | Sat | LSTM, Finish inverse Transform for normalization, save/load sklearn scaler
2022-11-13 | Sun
2022-11-14 | Mon | LSTM, try autotuner, RayTune | Done, but few errors to fix, not using gpu for some reason
2022-11-15 | Tue | LSTM, systematically train models with certain hyperparameters | fixed errors, pytorch raytune example was old code, using raytune tutorial now
2022-11-16 | Wed
2022-11-17 | Thu | LSTM, Write Evaluation, put figures in, check what to change in figures, create all chapter outlines and write rought summary for all of them
2022-11-18 | Fri | LSTM, Clean up evaluation/generate missing plots, identify what methods are needed to explain evaluation, write methods
2022-11-19 | Sat | LSTM, Write most of methods, LSTM, metrics/loss function
2022-11-20 | Sun | LSTM, Write creation of datasets, odes, normalization
2022-11-21 | Mon | LSTM, Write training theory, hyperparameter overview, hyperparameter search manually vs autotuner
2022-11-22 | Tue | Kann ich das glauben Seminar, go over presentation again
2022-11-23 | Wed | LSTM, Write "other work" chapter, introduction
2022-11-24 | Thu | LSTM, Clean up writing, check for things that need more work, make new plan for rest
2022-11-25 | Fri
2022-11-26 | Sat
2022-11-27 | Sun
2022-11-28 | Mon
2022-11-29 | Tue
2022-11-30 | Wed
2022-12-01 | Thu | Abgabe fast fertig
2022-12-02 | Fri
2022-12-03 | Sat
2022-12-04 | Sun
2022-12-05 | Mon
2022-12-06 | Tue
2022-12-07 | Wed | Abgabe final
2022-12-08 | Thu
2022-12-09 | Fri